## Slide 1
Village of
Hastings-on-Hudson
COMPREHENSIVE PLAN
UPDATE &
LOCAL WATERFRONT REVITALIZATION PROGRAM
Committee Meeting
May 22, 2024
James Harmon Community Center

## Slide 2
WELCOME

## Slide 3
  This presentation was prepared with funding provided by the New York State Department of State under Title 11 of the Environmental Protection Fund.

## Slide 4
AGENDA
  Approval of Meeting Summary
  Project Status Update
  Committee Comprehensive Plan Comments Presentation/Discussion
  Committee Consideration of Setting Public Hearing
  Committee Tasks and Next Steps
  Public Comment

## Slide 5
APPROVAL OF MEETING SUMMARIES
  April 10, 2024

## Slide 6
Summer/Fall 2023 / Winter 2024
Spring/ Summer 2024
Draft Plan Recs
Draft LWRP
3rd Round Public Engagement
Draft Comp Plan
Draft LWRP
Final Comprehensive Plan (Trustees)
Adoption of Plan (Trustees)
Summer/Fall 2024
Spring 2023
Winter 2022-23
Fall 2022
PROJECT STATUS UPDATE
*CPU Kick-off
Initiate Data Collection & Analysis
Public Participation Plan
Project Website
1st Round Public Engagement
Data Collection & Analysis
LWRP Policies
Comp Plan Vision & Goals
Comp Plan Strategies & Recommendations
LWRP Proposed Project & Uses
2nd Round Public Engagement
Committee Public Hearing
Revised Draft Comp Plan
Preliminary Draft LWRP

## Slide 7
    Remaining Key Committee Steps (Anticipated)
    May 2024
    3rd/Potential Final Committee Draft Comprehensive Plan
    Consider scheduling Committee Public Hearing
    July 2024 (?)
    Discuss edits to Final Committee Draft Comprehensive Plan
    Consider vote to forward Draft Comprehensive Plan to Board of Trustees
PROJECT STATUS UPDATE
      Following preparation of Final Committee Draft Comprehensive Plan, the Committee will vote forward the Final Draft Comprehensive Plan to the Village Board of Trustees to consider initiating the adoption process which is anticipated to include several steps such as:
      Village Board of Trustees Public Hearing
      Compliance with SEQRA
      GML 239-M County Planning Board Referral
      Plan Revisions as appropriate
      At the Committee Public Hearing, the public will have the opportunity to provide comment on the Draft Comprehensive Plan.
      Following the Committee Public Hearing, the Committee will consider public comment received and any additional edits to be incorporated into the plan.

## Slide 8
PROJECT STATUS UPDATE
    Remaining Committee Public Engagement (Anticipated)
    Public Engagement #4/Committee Public Hearing - TBD
      Summer 2024
      Draft Comprehensive Plan for public viewing in advance
      Committee Public Hearing on Draft Comprehensive Plan
      NOTE: The Village Board of Trustees is required to hold a public hearing on the draft plan prior to adoption.

## Slide 9
COMMITTEE COMPREHENSIVE PLAN COMMENTS PRESENTATION

## Slide 10
COMMITTEE COMPREHENSIVE PLAN COMMENTS PRESENTATION
Discussion Timeframes | 
Introduction: | 5 Minutes
Vision, Goals and Smart Growth Principles: | 5 Minutes
Village Overview: | 5 Minutes
History and Placemaking: | 5 Minutes
Housing: | 5 Minutes
Economic Vitality: | 5 Minutes
Sustainability and Resiliency: | 5 Minutes
Recreation: | 5 Minutes
Connectivity, Mobility and Access: | 5 Minutes
Waterfront: | 5 Minutes
Governance: | 5 Minutes
Implementation: | 5 Minutes
    Do the revised sections reflect your comments and/or the intent of your comments?
    Do you support sharing the draft Comprehensive Plan for public review and scheduling the Committee public hearing (with your minor edits on Version 3 or as discussed today)?
      Reminder: Following the Committee Public Hearing, an additional Committee meeting is anticipated to consider public comment received and any additional edits to be incorporated into the plan.

## Slide 11
DRAFT INTRODUCTION (5 Minutes)_
Reviewers:
Dave Gunton
Trustee Drake
Mary Beth Murphy
General Version 3 Comments Received:
Minor Formatting & Text Edits
Photo Updates

## Slide 12
DRAFT VISION, GOALS AND SMART GROWTH PRINCIPLES (5 Minutes)
Reviewers:
Chris Thomas
Edward Kuch
General Version 3 Comments Received:
No edits

## Slide 13
DRAFT VILLAGE OVERVIEW (5 Minutes)
Reviewers:
Trustee Drake
Meghann Donahue
Mary Beth Murphy
General Version 3 Comments Received:
Minor Text edits/clarification
Inclusion of Previous Accomplishments (?)

## Slide 14
DRAFT HISTORY AND PLACEMAKING (5 Minutes)
Reviewers:
Sarah Dupere Ostro
Meg Walker
Natalie Barry
Mary Beth Murphy
General Version 3 Comments Received:
Formatting & Text Edits
Minor content additions
Minor content edits/clarification
Minor Recommendation edits

## Slide 15
DRAFT HOUSING (5 Minutes)
Reviewers:
Chris Thomas
Dave Gunton
Mary Beth Murphy
General Version 3 Comments Received:
Include data reference
Minor text edits
Minor content clarifications
Formatting
Recommendation edits and modifications to descriptions

## Slide 16
DRAFT ECONOMIC VITALITY (5 Minutes)
Reviewers:
Richard Bass
Meghann Donahue
Mary Beth Murphy
General Version 3 Comments Received:
Minor text edits
Minor content clarifications
Minor Recommendation edits

## Slide 17
DRAFT SUSTAINABILITY AND RESILIENCY (5 Minutes)
Reviewers:
J. Patrick Diggins
Sarah Dupere Ostro
General Version 3 Comments Received:
Minor Recommendation Edits

## Slide 18
DRAFT RECREATION (5 Minutes)
Reviewers:
Samantha Merton
Edward Kuch
General Version 3 Comments Received:
Minor content addition
Text edits

## Slide 19
DRAFT CONNECTIVITY, MOBILITY AND ACCESS (5 Minutes)
Reviewers:
Samantha Merton
Natalie Barry
General Version 3 Comments Received:
Minor recommendation edits

## Slide 20
DRAFT WATERFRONT (5 Minutes)
Reviewers:
Meg Walker
J. Patrick Diggins
Trustee Fleisig
General Version 3 Comments Received:
Formatting & Text Edits
Minor content edits
Parcel graphic update

## Slide 21
DRAFT GOVERNANCE (5 Minutes)
Reviewers:
Mary Beth Murphy
Richard Bass
Trustee Fleisig
General Version 3 Comments Received:
Minor text edits
Minor content addition

## Slide 22
DRAFT IMPLEMENTATION (5 Minutes)
Reviewers:
Mary Beth Murphy
Trustee Fleisig
General Version 3 Comments Received:
Formatting & Text Edits
Minor content edits
Inclusion of Comprehensive Plan Oversight Committee Recommendation (?)

## Slide 23
Discussion of Public Meeting #4 / Committee Public Hearing
Public Meeting #4 - Committee Public Hearing
  This hearing will be scheduled once the Committee decides the draft Comprehensive Plan is ready for public review
  Formally noticed by Village
  Brief introductory presentation by MJ
  Public comment period
  Summary of public comments

## Slide 24
COMMITTEE TASKS & NEXT STEPS
  LWRP
  Section IV – in progress
  Comprehensive Plan
  Refinements to Version 3 Draft
  Potential Committee Public Hearing scheduled

## Slide 25
PUBLIC COMMENT